## Goods
PROCUREMENT PLAN
1 | General
| Country/Organization: | Arab Republic of Egypt
| Project/Programme Name | EMERGENCY HUMANITARIAN RELIEF ASSISTANCE TO THE VICTIMS OF THE FLOODS
Project/Programme SAP Identification #
Loan #:
Executing Agency:
Approval Date of Procurement Plan:
Date of General Procurement Notice:
Date GPN Published (UNDB):
Advance Contracting
Period Covered by the Proc. Plan From:
To :
Borrowers bid reference :
| Prior Review Threshold: | Procurement decisions subject to Prior Review by the Bank as
stated in Annex B5 of the Appraisal Report
GOODS
2 | Goods and Non-Consulting Services:
| Procurement Method | Prior review Threshold (UA equiv.) | Post review Threshold (UA equiv.) | Frequency of Review
| Shopping | ALL |  | Quarterly
3. | Procurement Packages with Methods and Time Schedule |  | BASIC DATA | [12 empty] | Bid Documents (Request for Quotations) |  | Pre-Qualification |  | Pre-Qualification |  | Bidding Period |  | Bid (Quotations) Evaluation |  | Contract Award | [5 empty] | Contract Implementation |  | Comments
| Package Number | Package Description* | SPN/IFP Date received | SPN/IFP Approval date | SPN/IFP Date Published | Lot Number | Lot Description | Issue # of Invitation for Bids | Total contract estimated amount in USD | Procurement Method | Pre-or Post Qualification | Dom/Reg. Preference (Y/N) | Prior or Post Review | Bid closing date | Plan vs. Actual | Date Proposed | Date No-objection | Doc Issued | Closing Date | Evaluation Report | No- objection | Bid Invitation Date | Bid Opening | Bid (Quotation) Evaluation Report | No- objection | Draft Received | Date No-objection | Contract Amount in USD | Date of Contract Award | Date of Contract Signature | Final Contract Received date | Start Date | End Date | Comments
Component 1:
| 1 | Goods | NA | NA | NA | NA | Goods | NA | 625000 | Direct Contracting |  |  | Prior |  | Plan | NA | NA | N/A | N/A | N/A | N/A | N/A | N/A | NA | NA | 31.1.2016 |  | 625000 | 5.2.2016 | 6.2.2016 |  | 6.2.2016 | 30.6.2016
[10 empty] | Direct Contracting |  |  |  |  | Revised
|  |  | NA | NA | NA | NA |  | NA |  | Direct Contracting |  |  |  |  | Actual | NA | NA | N/A | N/A | N/A | N/A | N/A | N/A | NA | NA | NA | NA
| Component 2: | Non consulting Services MOU | NA | NA | NA | NA | MOU | NA | 365000 | MOU |  |  | Prior |  | Plan | NA | NA | N/A | N/A | N/A | N/A | N/A | N/A | NA | NA | 28.1.2016 | 30.1.2016 | 365000 | NA | NA | NA | 10.2.2016 | 30.6.2016
[10 empty] | MOU |  |  |  |  | Revised
|  |  | NA | NA | NA | NA |  |  |  | MOU |  |  |  |  | Actual | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  | NA | NA | NA
| Total (USD) | [7 empty] | 990000
Note 1.
(Supplementary information concerning
Procurement of Goods and Non-Consultancy services, such as Pre-qualification
or any other Special Procurement Arrangements)

## Consultants
PROCUREMENT PLAN
1 | General
| Country/Organisation: | Arab Republic of Egypt | Ministry of International Cooperation
| Project/Programme Name | EMERGENCY HUMANITARIAN RELIEF ASSISTANCE TO THE VICTIMS OF THE FLOODS
| Project/Programme SAP Identification # | MIC TAF
Loan #:
| Executing Agency: | Ministry of International Cooperation
Approval Date of Procurement Plan:
Date of General Procurement Notice:
Date GPN Published (UNDB):
| Advance Contracting | Yes
Firm or Individual
| Period Covered by the Proc. Plan From: | November 15, 2014
| To: | March 31, 2015
Borrowers bid reference :
| Prior Review Threshold: | Procurement decisions subject to Prior Review by the Bank as
stated in Annex B5 of the Appraisal Report
CONSULTANTS
2 | Consultancy services
| Procurement Method | Prior review Threshold (USD) | Post review Threshold (USD) | Frequency of Review
| Quality-and-Cost Based Selection (QCBS) | ALL | <100,000 | Quarterly
| Least-Cost Selection (LCS) | ALL | <100,000 | Quarterly
| Single-Source Selction(SSS) | ALL |  | Quarterly
| Individual Concultant(IC) | First Contract | All | Quarterly
3 | Procurement Packages with Methods and Time Schedule |  | Basic Data | [5 empty] | Terms Of Reference |  | Request for Expression of Interest |  | Short List |  |  | Request for Proposal |  | Bid Proposals |  | Bid Evaluation Technical (T) & Financial (F) |  |  |  | Contract Award | [5 empty] | Contract Implementation |  | Comnents
| Package Number | Package Description | Selection Method | Lumpsum or Time-Based | Total Estimated Amount in USD | Prior/Post Review | Bid closing date | Plan vs. Actual | Date Proposed | Date No-objection | Date Pubished | Closing Date | Date Proposed | Date No-objection | Plan vs. Actual | Date Prepared | Date No- objection | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Plan vs. Actual | Eval Report (T) & (F) Draft Received | Date No-objection | Contract Amount in USD | Date of Contract Award | Date of Contract Signature | Final Contract Received date | Start Date | End Date | Comnents
Component 3: Consulting Services
| 1 | Independent external audit | Consultants' Qualifications (CQS) | Lump Sum Contract | 10000 | Prior | NA | Plan | 1.10.2016 | 5.10.2016 | NA | NA | NA | N/A | Plan | 7.10.2016 | NA | 15.10.2016 | 10.11.2016 | NA | NA | 15.11.2016 | Plan | 17.11.2016 | 20.11.2016 | 10000 | 22.11.2016 | 23.11.2016 |  | 23.11.2016 | 31.12.2016
|  |  | Consultants' Qualifications (CQS) | Lump Sum Contract |  |  | NA | Revised |  |  | NA | NA | NA | N/A | Revised |  | NA | [5 empty] | Revised
|  |  | Consultants' Qualifications (CQS) | Lump Sum Contract |  |  |  | Actual | [6 empty] | Actual | [7 empty] | Actual

## Goods Web Template (hidden)
PROCUREMENT PLAN
1 | General | Fill gray cells only!
| Country/Organisation: | =Goods!C4
| Project/Programme Name | =Goods!C5
Project/Programme SAP Identification #
| Loan Number | x
| Executing Agency: | x
| Approval Date of Procurement Plan: | x
| Date of General Procurement Notice: | x
Period Covered by these Proc. Plans:
| Prior Review Threshold: | Procurement decisions subject to Prior Review by the Bank as
stated in Annex B5 of the Appraisal Report
GOODS
2 | Goods and Non-Consulting Services (see Note 1)
| Procurement Method | Prior review Threshold '(UA equiv.) | Post review Threshold '(UA equiv.) | Frequency of Review
| 1 ICB | =Consultants!C20
| 2. NCB | =Consultants!D31
3.
4.
5.
6.
3. | Procurement Packages with Methods and Time Schedule for 18 months | BASIC DATA
| Description* | Lot Number | SPN/IFP Publication Date | Estimated Amount in Currcy. (000) | Procurement Method | Pre-Qualification (Y/N) | Dom/Reg. Preference (Y/N) | Prior or Post Review | Contract Start Date | Advance Contracting | Comments
| Total Cost |  |  | 0
Note 1. (Supplementary information concerning Procurement of Goods and Non-Consultancy services, such as Pre-qualification or any other Special Procurement Arrangement)